## Sheet1
SIA 101 Project Development Gantt Chart
Project Name: | Web-Based Homestay Booking and Management System for EAVs Homestay
Project Developer: | CETRIN JR. M. VALDEHUEZA
Project Start: | 2026-08-20
Current Date: | 2026-10-19
Weeks in Progress: | 9
[5 empty] | 2026-08-20 | 2026-08-27 | 2026-09-03 | 2026-09-10 | 2026-09-17 | 2026-09-24 | 2026-10-01 | 2026-10-08 | 2026-10-15 | 2026-10-22 | 2026-10-29 | 2026-11-05 | 2026-11-12 | 2026-11-19 | 2026-11-26 | 2026-12-03 | 2026-12-10 | 2026-12-17
Task/Phase | Start Date | End Date | Duration (Days) | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
Phase 1: Planning & Requirements
Task 1: Client Interview & Requirements Gathering | 2026-08-20 | 2026-08-30 | 10 | 100%
Task 2: Gantt Chart & Project Planning | 2026-08-31 | 2026-09-06 | 6 | 100%
Phase 2: Architectural & UI Design
Task 3: Database Design (ERD) & Architecture | 2026-09-07 | 2026-09-20 | 13 | 90%
Task 4: UI Mockups & Wireframing | 2026-09-21 | 2026-09-28 | 7 | 0%
Midterm Exam | 2026-09-29 | 2026-10-03 | 4
Phase 3: Core System Development
Task 5: Frontend Development (Guest Website) | 2026-10-05 | 2026-10-18 | 13 | 95%
Task 6: Backend Development (Admin Dashboard) | 2026-10-19 | 2026-11-01 | 13 | 90%
Phase 4: Systems Integration
Task 7: Booking Engine & Calendar Setup | 2026-11-02 | 2026-11-25 | 23 | 80%
Task 8: External API Integrations (Maps/Payments) | 2026-11-16 | 2026-11-22 | 6 | 0%
Phase 5: Testing & Quality Assurance
Task 9: System Bug Testing | 2026-11-23 | 2026-11-27 | 4 | 30%
Task 10: User Acceptance Testing (with your Uncle) | 2026-11-28 | 2026-11-30 | 2 | 0%
Final Exam | 2026-12-01 | 2026-12-05 | 4
Phase 6: Finalization & Deployment
Task 11: System Hosting & Deployment | 2026-12-07 | 2026-12-11 | 4 | 0%
Task 12: Final Documentation & Presentation Prep | 2026-12-12 | 2026-12-18 | 6 | 50%
Note on B4: user: Insert Start Date